## Sheet1
Typical Samples for Sprint #1
What is the problem? | Which alternatives have been considered? | Which alternative has been selected? | Additional Justification (optional)
Which application framework are we going to use? | * JavaFX, * JavaEE, * Spring | Spring
How are we going to implement our data base server? | * Create a data base on an external server; * Create a local HSQLDB instance within the application | Local HSQLDB instance within the application
Which CI (continuous integration) server are we going to use? | * Jenkins * Travis * Codeship | Jenkins
What is the target development platform for our application? | * Android * Web Application | Web Application
What is the target development platform for our application? | * Android * Windows Desktop | Android | Android is the better choice, because of its high availability, and low resource consumption.
How are we going to deploy the CI (continuous integration) server? | * Deploy it on an externally run server * Locally deploy a CI server instance | Limit the CI (continuous integration) functionality to a locally run CI server.
How are we going to organise the Code Review | * No code review at all * Code review is conducted by one person * Code reviews are conducted by at least two persons | Code reviews are conducted by at least two persons
How are we going to organise the communication within the team? | * Via teamspeak + Facebook chat + Google docs * Only via redmine (tool) * Additional personal meetings | Via teamspeak + Facebook chat + Google docs
Which test framework are we going to use? | * We do not use test frameworks, we test manually. * Use the Espresso Test Framework * Use the Robotium Test Framework | Use the Espresso Test Framework
Which REST framework are we going to use? | * Django * Play * Dropwizard * Jersey | Django
What is our data exchange format? | * JSON * XML * Raw data | JSON
What programming language are we going to use? | * C++ * Java | Java
How are we going to deploy our Android application? → How will the customer receive the product increments? | * Android device → Native * Emulator | Emulator
Which IDE are we going to use? | * IntelliJ * Eclipse * Netbeans | IntelliJ | * IDE IntelliJ - integrates many useful tools is very powerful, very good support for writing code and the number of procedures concerning the building project is done automatically. Unfortunately, the team had put considerable effort into adapting to this IDE. * Netbeans - considered as an alternative because of our experience of working in this environment with other tasks; Unfortunately, it turned out to have poor support for chosen development framework * Eclipse - considered because we already used in other development labs; however, it has been rejected due to lack of support for the chosen development framework.
How are we going to organise the team work? | * Individual work at home + communication tools * Meet and work together in groups | Individual work at home + communication tools
Typical Samples for Sprint #2
What is the problem? | Which alternatives have been considered? | Which alternative has been selected? | Additional Justification (optional)
How are we going to develop our CSS files? | * Write our own CSS files. * Use CSS template files that you can easily find in the internet. | Write our own CSS files. | Although our CSS skills are not at the highest level we decided that the creation of CSS files will help us to improve our CSS skills.
How are we going to distribute the development tasks ahead of us? | * Everybody is going to deal with every aspect of the application to come. * Clear division of labour. Every team member is responsible for one of the four major aspects of the application (database, documentation, feature implementation, test, user experience) | Clear division of labour. | We considered that each of us will deal with every aspect of the application to some extent. However, this is not the best idea. It will consume much more time until completion compared to a strict division of labour.
How do we deal with change request from within the team? | * Everybody is applying the required changes him/her self. * Set up a change request and wait for the author of the code to consider and service this change request. | Work with change requests. | If everybody is free to change code as desired, this will end up in a mess within the code.
Our front is full of bugs. | * We reconstruct our fronent using ReactJS. * We stay with the current implementation and try to fix the bugs. | We reconstruct our fronent using ReactJS.
How do integrate Captchas in our software? | * Use reCaptcha from Google * Implement an own Captcha solution | Use reCaptcha from Google
Which IDE are we going to use? | * Eclipse * Text editor + maven | Text editor + maven
What is the target development platform for our application? | * Java desktop application * Web application | Java desktop application
Which driver are we going to use to communicate with the data base? | * Xerial implementation of the JDBC driver * Zentus implementation of the JDBC driver | Xerial implementation of the JDBC driver
Our current approach of conducted meetings does not work. The communication within the team is insufficient. | * Maintain a regular daily scrum. * Conduct more group meetings to communicate and to do pair programming | Maintain a regular daily scrum. | We need to maintain a regular daily scrum - this will solve the problem of lack of coordination in carrying out tasks that depend on each other, we will better meet deadlines and strengthen a common vision of the project (to resolve the disparities between certain team members).
What is the main aspect of this sprint? | * Data base implementation * Implement Continous deployment * Data security | Data Security
The user experience is unpleasant. | * Redesign the UI. * Stick with the current UI. | Redesign the UI.
How are going to test our software? | * Write tests at the end * Continuously write tests | Continuously write tests
Is the application platform still fitting our needs? | * Stick with Android as application platform * Transform our application into a web application | Stick with Android
Do we use branching in git? | * Use a separate branch per task. * Commit all tasks to the same branch. | Use a separate branch per task. | We could do it the same way as we did it in the previous sprint, i.e. all jobs are committed to one branch and are subsequently tested. Unfortunately this sometimes led to errors. This stopped us from working on subsequent tasks.
How are we going to integrate states into our code? | * Use constants + strategy pattern * Completely abandon states * Keep them in the data base | Use constants + strategy pattern
Typical Samples for Sprint #3
What is the problem? | Which alternatives have been considered? | Which alternative has been selected? | Additional Justification (optional)
How are we going to display charts? | * Use Google charts * Implement our own solution | Use Google charts
How are we going to avoid mistakes in the future? | * Prepare a personal list of mistakes made in the past. * Do not learn from the current project and ignore recent experiences. | Prepare a personal list of mistakes made in the past.
How are we going to measure the performance of our app? | * We use MonkeyRunner (im combination with Espresso) * We use Jmeter | Monkeyrunner
How are going to test our software? | * Automates tests * Manual tests | Manual test | Our interface is too simple to an advances software for testing
How are we going to distribute the development tasks ahead of us? | * Keep the current distribution of work * Shift one person from the backend to the frontend | Shift one person from the backend to the frontend | Change is necessary in order to speed up the work
We won’t manage to implement all features until the end of the project. | * Try to realize everything until the end of the semester * Dispense unnecessary features | Dispense unnecessary features
How do we test our software? | * Test models and simple things. * Test with mocks and testing controllers. | Test with mocks and testing controllers.
How do we test our software? | * Use Selenium IDE * Use NightwatchJS as a testing framework. | Selenium IDE | Despite the many difficulties in forcing the Selenium IDE to work with our project, we did not want to change the software for testing
How do we perform acceptance tests? | * Robotium * SelenDroid * UIAutomator * TestDroid | Robotium
How do we realise new functionality in our game software? | * Extend the data base * Integrate the new data into the runtime. | Integrate the new data into the runtime.
How do we inform the team of our current work? | * Prepare weekly work reports. * Hold meetings. | Prepare weekly work reports.
How do we divide the work? | * Divide the work equally within the team. * Divide the work by the contributions already made. * Divide the work as required with the team. | Divide the work equally within the team.
How do organise our work? | * Change our working hours and introduce greater regularity * Increase the frequency of meetings and reduce their duration | Increase the frequency of meetings and reduce their duration
How do we carry out our acceptance test? | * Using Cucumber. * Ruby toolbox. | Ruby toolbox.